Terms of Reference

for Project Location Data Collection and Management 
as part of Project Reporting

- General requirements:

The project location data will form part of the regular project implementation reporting of the present Financial Cooperation (FC) project (see: Agreement on Reporting Requirements of The Project Executing Agency (PEA)) and shall be attached as an annex to each progress report, starting with the project inception report and ending with the final report, if not explicitly specified otherwise. Therefore, the project location data is to be collected, managed and quality-assured by the same party/parties who are responsible for project reporting in general and to be distributed to the parties receiving the project reports, i.e. all relevant stakeholders. They are to be provided and updated with the following general requirements:

- The project location data is to be submitted as an annex to the word or pdf-version of the report in a specific standardized file format provided as part of the present ToR on the following website: https://mapme-initiative.github.io/project_location_model/annex1.html

  - The provided Excel template requires the provision of standard project data in accordance with the common requirements (chapter 2) of the general KfW reporting requirements. All data fields are mandatory.

  - All planned or existing project locations with their main activities and respective attributes and coordinates shall be inserted into the template row by row. One row is equivalent to one project location. In case it is not self-evident how the locations of the project are to be defined (e.g. in some cases, it makes sense to summarize a number of small sites or various activities in one community under one project location, in other cases it doesn’t), this shall be clarified in advance with the recipient parties of the project reports.

  - For each project location there should be one exact or approximate geolocation dataset, which is to be updated in the above-stated regular reporting intervals. The Details are explained in KfW’s Project Location Model itself (see link above).

  - If a Geographic Information System (GIS) or equivalent is used in the project, then the existing location IDs should be entered also in the Excel template in the Column ”location name” as part of the location name in the project location data Excel template. Equally, if lines or polygon data is submitted, the “location name” must be uniquely defined in each row, so that coordinates can be assigned correctly. Such uniquely defined location name IDs make it easier to check location data across project partner systems and verify the use of funds.

  - The frequency of location data reporting and changes corresponds to the general KfW reporting requirements (chapter 6.1: Progress of Services and Works): annually or bi-annually, depending on the type of project, and if not otherwise agreed by the PEA and KfW.

  - Before submitting an update of the location data to KfW, please check on the above website for the latest version of the data model template. Only the current template version will pass the automatic validator, also provided on the website. Only submit project location data, which has been screened with the online location validator and is error free.

- After submitting the first set of site data / Excel file, unique KfW identifiers (= Field IDs) will be assigned to the sites in the project location template in column A.

- All additional reported information that is related to the project location(s), including photos, videos, satellite images and maps shall state the respective BMZ-number, timestamp, and related coordinates, and if already available, the Field ID (=KfW identifier) provided by KfW.

- Data consistency

- It is the task of the PEA and their Project Implementation Consultant to ensure correct and standardised data input (e.g. correct coordinates in the requested format for polygons, lines or points using the precise syntax).

- The data fields, columns and / or formulas of the Excel template shall not be changed. Additional information can only be provided using additional columns at the end of the table (to the right) or via the related geographic file format, if so agreed with KfW and the PEA.

- It is the PEA’s and their Project Implementation Consultant’s responsibility to provide a fully functional location data file in the appropriate format and according to the latest template provided on the above website with all data fields filled out and fully functioning formulas.

- Data security and privacy

- Europe-based Consultants or Project Executing Agencies / Implementing Partners or Consultants working directly for KfW are legally required to ensure compliance of data collection including websites and software both with the relevant national regulations of the country in which the data is being collected as well as with the General Data Protection Regulation (GDPR, in German called DSGVO). All other data providers are required to adhere to the relevant national regulations of the country in which the data is being collected.

- Data shall only be transferred through encrypted channels (e.g. idgard).

- Special caution is required in fragile and conflict contexts, where location data should be treated with extra diligence, e.g. working only with approximate geo coordinates for security reasons.

KfW’s Project Location Model Documentation https://mapme-initiative.github.io/project_location_model/quickstart.html including its Templates and Guidelines under the same link are part of these ToR.